## Transformation Roadmap
# | Phase | Workstream | Step / Area | Task | Owner (TransformAZ) | Owner (Taylor) | Support | Output / Deliverable | Priority | Dimension | C/B/E | Start Date | End Date | Status | Days
PHASE 0 — PRE-ENGAGEMENT
1 | Phase 0 | Scope | Transformation Scope Definition | Define transformation objectives with leadership | Fermin | Executive Sponsor | — | Agreed transformation objectives | High | Processes | ALL | 2026-03-18 | 2026-03-22 | Not Started
2 | Phase 0 | Scope | Transformation Scope Definition | Define workstreams in scope (Ops, Tech, Org, etc.) | Fermin | Leadership Team | — | Workstreams defined | High | Processes | ALL | 2026-03-20 | 2026-03-25 | Not Started
3 | Phase 0 | Scope | Transformation Scope Definition | Define deliverables by phase | Fermin | — | — | Deliverables framework | High | Processes | ALL | 2026-03-22 | 2026-03-27 | Not Started
4 | Phase 0 | Scope | Scope Alignment | Align expectations with executive team | Fermin | Executive Sponsor | — | Scope alignment confirmed | High | People & Culture | ALL | 2026-03-25 | 2026-03-31 | Not Started
5 | Phase 0 | Scope | Scope Documentation | Draft scope document | Fermin | — | — | Scope document v1 | High | Processes | ALL | 2026-03-28 | 2026-04-02 | Not Started
6 | Phase 0 | Scope | Scope Documentation | Finalize and validate scope | Fermin | Executive Sponsor | — | Final scope document | High | Processes | ALL | 2026-04-02 | 2026-04-05 | Not Started
7 | Phase 0 | Governance | Governance Design | Define governance structure (Sponsor, SteerCo, etc.) | Fermin | Executive Sponsor | — | Governance model defined | High | Compliance | ALL | 2026-03-25 | 2026-03-30 | Not Started
8 | Phase 0 | Governance | Governance Design | Define decision-making framework | Fermin | Leadership Team | — | Decision model defined | High | Compliance | ALL | 2026-03-27 | 2026-04-02 | Not Started
9 | Phase 0 | Governance | Cadence & Communication | Define meeting cadence | Fermin | — | — | Meeting cadence defined | Medium | Processes | ALL | 2026-03-30 | 2026-04-03 | Not Started
10 | Phase 0 | Governance | Cadence & Communication | Define communication channels & formats | Fermin | — | — | Communication model | Medium | Processes | ALL | 2026-03-30 | 2026-04-04 | Not Started
11 | Phase 0 | Ways of Working | SLA Definition | Define response times & turnaround expectations | Fermin | Ops / Key Stakeholders | — | SLA defined | High | Processes | ALL | 2026-04-01 | 2026-04-05 | Not Started
12 | Phase 0 | Ways of Working | Tools & Collaboration | Define tools (Drive, Asana, Slack, etc.) | Fermin | IT / Ops | — | Tools stack agreed | Medium | Tech Integrations | ALL | 2026-04-01 | 2026-04-06 | Not Started
13 | Phase 0 | Ways of Working | Working Model | Define sync vs async model | Fermin | — | — | Ways of Working doc | High | Processes | ALL | 2026-04-02 | 2026-04-07 | Not Started
14 | Phase 0 | Staffing | Team Structure | Define team structure (Project Lead, Workstream Leads, Analysts) | Fermin | — | — | Team structure defined | High | People & Culture | ALL | 2026-03-28 | 2026-04-02 | Not Started
15 | Phase 0 | Staffing | Resource Allocation | Define allocation by phase | Fermin | — | — | Allocation plan | High | People & Culture | ALL | 2026-04-01 | 2026-04-06 | Not Started
16 | Phase 0 | Staffing | Internal Alignment | Confirm availability of key resources | Fermin | — | Internal Team | Resource confirmation | High | People & Culture | ALL | 2026-04-03 | 2026-04-08 | Not Started
17 | Phase 0 | Contract | Commercial Model | Define pricing model | Fermin | — | — | Pricing structure | High | Processes | ALL | 2026-03-25 | 2026-03-30 | Not Started
18 | Phase 0 | Contract | Contract Drafting | Draft agreement | Fermin | Legal | Legal | Draft contract | High | Compliance | ALL | 2026-03-30 | 2026-04-05 | Not Started
19 | Phase 0 | Contract | Negotiation | Align terms with client | Fermin | Legal / Sponsor | — | Terms agreed | High | Compliance | ALL | 2026-04-05 | 2026-04-12 | Not Started
20 | Phase 0 | Contract | Signature | Execute contract | Fermin | Executive Sponsor | — | Signed agreement | Critical | Compliance | ALL | 2026-04-10 | 2026-04-15 | Not Started
PHASE 1 — INTAKE (Remote)
21 | Phase 1 | Data Room Setup | Structure Definition | Define data room structure | Fermin | IT / Ops | — | Data room architecture defined | High | Data | CREATE | 2026-05-01 | 2026-05-05 | Not Started
22 | Phase 1 | Data Room Setup | Repository Setup | Set up data room repository (Drive/Notion/etc.) | Fermin | IT / Ops | — | Data room live | High | Tech Integrations | CREATE | 2026-05-03 | 2026-05-09 | Not Started
23 | Phase 1 | Information Request | Request Framework | Define information request framework | Fermin | — | — | Structured request template | High | Processes | CREATE | 2026-05-01 | 2026-05-07 | Not Started
24 | Phase 1 | Information Request | Data Collection | Send structured information request to Taylor | Fermin | Executive Sponsor | — | Information request sent | High | Processes | CREATE | 2026-05-07 | 2026-05-09 | Not Started
25 | Phase 1 | Information Request | Data Collection | Collect SOPs and process documentation | Fermin | Ops / Team Leads | — | SOP repository | High | Processes | CREATE | 2026-05-09 | 2026-05-30 | Not Started
26 | Phase 1 | Information Request | Data Collection | Collect org charts and role definitions | Fermin | HR / Leadership | — | Org structure documentation | High | People & Culture | CREATE | 2026-05-09 | 2026-05-24 | Not Started
27 | Phase 1 | Information Request | Data Collection | Collect tech stack and systems overview | Fermin | IT | — | Systems inventory | High | Tech Integrations | CREATE | 2026-05-09 | 2026-05-24 | Not Started
28 | Phase 1 | Information Request | Data Collection | Collect asset inventory and warehouse data | Fermin | Ops / Warehouse | — | Asset baseline data | High | Data | BUILD | 2026-05-09 | 2026-05-30 | Not Started
29 | Phase 1 | Information Request | Data Collection | Collect financial & project profitability data | Fermin | Finance / Leadership | — | Financial baseline | Medium | Data | EXECUTE | 2026-05-13 | 2026-05-30 | Not Started
30 | Phase 1 | Access & Systems | Access Provisioning | Provide system access (ClickUp, M365, Gemini) | — | IT / Ops | — | Access granted to systems | Critical | Tech Integrations | CREATE | 2026-05-09 | 2026-05-20 | Not Started
31 | Phase 1 | Access & Systems | Tools Familiarization | Access and explore systems (ClickUp, M365, Gemini) | Fermin | — | — | Initial system understanding | High | Tech Integrations | CREATE | 2026-05-11 | 2026-05-30 | Not Started
32 | Phase 1 | Access & Systems | Tools Familiarization | Audit ClickUp workspace architecture & Brain status | Fermin | — | — | ClickUp audit report | High | Tech Integrations | BUILD | 2026-05-15 | 2026-05-30 | Not Started
33 | Phase 1 | Access & Systems | Tools Familiarization | Audit Gemini deployment and usage patterns | Fermin | — | — | Gemini audit report | High | Tech Integrations | BUILD | 2026-05-15 | 2026-05-30 | Not Started
34 | Phase 1 | Documentation Review | Process Review | Review SOPs and process documentation | Fermin | — | — | Process insights documented | High | Processes | CREATE | 2026-05-15 | 2026-06-09 | Not Started
35 | Phase 1 | Documentation Review | Org & Decision Review | Review org structure, roles, and decision flows | Fermin | — | — | Org insights documented | High | People & Culture | CREATE | 2026-05-15 | 2026-06-05 | Not Started
36 | Phase 1 | Documentation Review | Data & Communication Review | Review systems, data flows, and integrations | Fermin | — | — | Systems insights documented | High | Tech Integrations | CREATE | 2026-05-20 | 2026-06-09 | Not Started
37 | Phase 1 | Documentation Review | Communication Review | Analyze email/communication patterns and volume | Fermin | — | — | Communication pattern analysis | High | Processes | EXECUTE | 2026-05-20 | 2026-06-05 | Not Started
38 | Phase 1 | Maturity Assessment | Dimension Scoring | Score current maturity: People & Culture (Deloitte Hexagon) | Fermin | — | — | People maturity score (1-5) | High | People & Culture | CREATE | 2026-05-30 | 2026-06-13 | Not Started
39 | Phase 1 | Maturity Assessment | Dimension Scoring | Score current maturity: Processes | Fermin | — | — | Process maturity score (1-5) | High | Processes | CREATE | 2026-05-30 | 2026-06-13 | Not Started
40 | Phase 1 | Maturity Assessment | Dimension Scoring | Score current maturity: Tech Integrations | Fermin | — | — | Tech maturity score (1-5) | High | Tech Integrations | CREATE | 2026-05-30 | 2026-06-13 | Not Started
41 | Phase 1 | Maturity Assessment | Dimension Scoring | Score current maturity: Data | Fermin | — | — | Data maturity score (1-5) | High | Data | CREATE | 2026-05-30 | 2026-06-13 | Not Started
42 | Phase 1 | Maturity Assessment | Dimension Scoring | Score current maturity: Compliance & Governance | Fermin | — | — | Compliance maturity score (1-5) | High | Compliance | CREATE | 2026-05-30 | 2026-06-13 | Not Started
43 | Phase 1 | Maturity Assessment | Baseline Report | Compile transformation baseline scorecard (BCG DAI-inspired) | Fermin | — | — | Transformation Scorecard v1 | Critical | Data | CREATE | 2026-06-13 | 2026-06-26 | Not Started
44 | Phase 1 | Initial Mapping & Hypotheses | Workflow Mapping | Map core workflows (initial) | Fermin | — | — | Initial workflow maps | High | Processes | CREATE | 2026-05-30 | 2026-06-20 | Not Started
45 | Phase 1 | Initial Mapping & Hypotheses | Decision Mapping | Map decision-making flows | Fermin | — | — | Decision flow maps | High | Processes | CREATE | 2026-05-30 | 2026-06-20 | Not Started
46 | Phase 1 | Initial Mapping & Hypotheses | Hypothesis Building | Build initial hypotheses (gaps, frictions) | Fermin | — | — | Hypothesis set v1 | High | Processes | CREATE | 2026-06-09 | 2026-06-26 | Not Started
47 | Phase 1 | Initial Mapping & Hypotheses | Hypothesis Building | Identify no-regret moves / quick wins (BCG approach) | Fermin | — | — | Quick wins shortlist | High | Tech Integrations | BUILD | 2026-06-13 | 2026-06-26 | Not Started
48 | Phase 1 | Initial Mapping & Hypotheses | Discovery Planning | Define discovery plan (interviews, on-site focus) | Fermin | Executive Sponsor | — | Discovery plan defined | Critical | Processes | CREATE | 2026-06-20 | 2026-06-30 | Not Started
PHASE 2 — DISCOVERY (Onsite Toronto + Remote)
49 | Phase 2 | Discovery Planning | Planning & Coordination | Finalize discovery agenda and schedule | Fermin | Executive Sponsor | Ops / HR | Confirmed agenda & calendar | High | Processes | CREATE | 2026-07-01 | 2026-07-05 | Not Started
50 | Phase 2 | Discovery Planning | Planning & Coordination | Confirm stakeholder participation (interviews & sessions) | Fermin | HR / Leadership | — | Stakeholder list confirmed | High | People & Culture | CREATE | 2026-07-02 | 2026-07-06 | Not Started
51 | Phase 2 | Discovery Planning | Planning & Coordination | Prepare interview guides (role-specific, dimension-mapped) | Fermin | — | — | Interview guides by role | High | People & Culture | CREATE | 2026-07-03 | 2026-07-06 | Not Started
52 | Phase 2 | On-site Execution | Kickoff | Conduct kickoff session (Discovery phase) | Fermin | Executive Sponsor | Leadership Team | Discovery kickoff completed | High | People & Culture | CREATE | 2026-07-07 | 2026-07-07 | Not Started
53 | Phase 2 | Interviews | Executive Interviews | Conduct leadership interviews (Dean, Mike, VPs) | Fermin | Leadership Team | — | Leadership insights documented | Critical | People & Culture | CREATE | 2026-07-07 | 2026-07-14 | Not Started
54 | Phase 2 | Interviews | Functional Interviews | Conduct functional/team interviews (Ops, Creative, Sales, IT) | Fermin | Team Leads | — | Functional insights documented | Critical | Processes | CREATE | 2026-07-08 | 2026-07-18 | Not Started
55 | Phase 2 | Interviews | Functional Interviews | Conduct cross-office interviews (Boston, Cleveland — remote) | Fermin | Office Leads | — | Cross-office insights | High | People & Culture | CREATE | 2026-07-10 | 2026-07-18 | Not Started
56 | Phase 2 | On-site Execution | Operational Observation | Observe operations on-site (incl. warehouse) | Fermin | Ops Team | — | Operational observations documented | Critical | Processes | BUILD | 2026-07-08 | 2026-07-18 | Not Started
57 | Phase 2 | On-site Execution | Operational Observation | Shadow key workflows: sales-to-production handoff | Fermin | Sales / Production | — | Handoff friction map | High | Processes | BUILD | 2026-07-09 | 2026-07-15 | Not Started
58 | Phase 2 | On-site Execution | Operational Observation | Observe asset management & warehouse operations | Fermin | Warehouse / Ops | — | Asset workflow observations | High | Data | BUILD | 2026-07-10 | 2026-07-16 | Not Started
59 | Phase 2 | On-site Execution | Technology Assessment | Hands-on ClickUp usage assessment with teams | Fermin | IT / Key Users | — | ClickUp usage patterns report | High | Tech Integrations | BUILD | 2026-07-09 | 2026-07-16 | Not Started
60 | Phase 2 | On-site Execution | Technology Assessment | Assess Gemini/M365 actual usage vs. potential | Fermin | IT / Key Users | — | AI tools gap analysis | High | Tech Integrations | BUILD | 2026-07-10 | 2026-07-16 | Not Started
61 | Phase 2 | On-site Execution | Culture & Adoption Assessment | Assess generational adoption readiness (Deloitte Talent dimension) | Fermin | HR / Team Leads | — | Adoption readiness matrix | High | People & Culture | CREATE | 2026-07-10 | 2026-07-18 | Not Started
62 | Phase 2 | On-site Execution | Culture & Adoption Assessment | Identify potential internal champions (3-5 per dept) | Fermin | Leadership / HR | — | Champion candidate list | High | People & Culture | CREATE | 2026-07-12 | 2026-07-18 | Not Started
63 | Phase 2 | Validation | Workflow Validation | Validate workflows with teams | Fermin | Team Leads | — | Validated workflow maps | High | Processes | BUILD | 2026-07-12 | 2026-07-22 | Not Started
64 | Phase 2 | Validation | Decision Validation | Validate decision-making processes | Fermin | Leadership Team | — | Validated decision maps | High | Processes | BUILD | 2026-07-12 | 2026-07-22 | Not Started
65 | Phase 2 | Validation | Systems Validation | Validate systems usage and gaps | Fermin | IT / Ops | — | Systems validation insights | High | Tech Integrations | BUILD | 2026-07-12 | 2026-07-22 | Not Started
66 | Phase 2 | Validation | Data Validation | Validate data flows and quality gaps | Fermin | IT / Finance | — | Data quality assessment | High | Data | BUILD | 2026-07-14 | 2026-07-22 | Not Started
67 | Phase 2 | Analysis | Gap Identification | Identify gaps, redundancies and breakdowns | Fermin | — | — | Gap analysis draft | Critical | Processes | CREATE | 2026-07-18 | 2026-07-25 | Not Started
68 | Phase 2 | Analysis | Gap Identification | Map gaps to 5 transformation dimensions (Deloitte Hexagon) | Fermin | — | — | Dimension-mapped gap matrix | High | Data | CREATE | 2026-07-20 | 2026-07-27 | Not Started
69 | Phase 2 | Interviews | Follow-up Interviews | Conduct follow-up interviews (remote/hybrid) | Fermin | Stakeholders | — | Additional insights captured | Medium | People & Culture | CREATE | 2026-07-20 | 2026-07-30 | Not Started
70 | Phase 2 | Analysis | Prioritization | Prioritize initiatives: no-regret moves vs. strategic bets (BCG) | Fermin | — | — | Prioritized initiative roadmap | Critical | Processes | CREATE | 2026-07-22 | 2026-07-30 | Not Started
71 | Phase 2 | Analysis | Prioritization | Define lighthouse projects for Phase 3 (McKinsey approach) | Fermin | — | — | Lighthouse project definitions | Critical | Tech Integrations | BUILD | 2026-07-25 | 2026-08-01 | Not Started
72 | Phase 2 | Analysis | Synthesis | Consolidate discovery findings | Fermin | — | — | Consolidated findings | Critical | Data | CREATE | 2026-07-25 | 2026-08-01 | Not Started
73 | Phase 2 | Analysis | Synthesis | Update transformation scorecard (post-Discovery) | Fermin | — | — | Transformation Scorecard v2 | High | Data | CREATE | 2026-07-28 | 2026-08-04 | Not Started
74 | Phase 2 | Validation | Executive Validation | Validate findings with leadership | Fermin | Executive Sponsor | Leadership Team | Validated findings | Critical | People & Culture | CREATE | 2026-08-01 | 2026-08-06 | Not Started
75 | Phase 2 | Reporting | Reporting | Draft current state report | Fermin | — | — | Current state report v1 | High | Data | CREATE | 2026-08-04 | 2026-08-11 | Not Started
76 | Phase 2 | Reporting | Reporting | Draft implementation roadmap & workstream plan | Fermin | — | — | Implementation roadmap v1 | Critical | Processes | BUILD | 2026-08-06 | 2026-08-14 | Not Started
77 | Phase 2 | Reporting | Reporting | Finalize current state & diagnosis report | Fermin | Executive Sponsor | — | Final diagnosis report | Critical | Data | CREATE | 2026-08-11 | 2026-08-30 | Not Started
PHASE 3 — IMPLEMENTATION (Hybrid)
78 | Phase 3 | Lighthouse Projects | Email & Communication | Deploy Gemini email triage for executive team (Dean, Mike) | Fermin | IT / Executives | — | Gemini email triage live | Critical | Tech Integrations | EXECUTE | 2026-09-01 | 2026-09-16 | Not Started
79 | Phase 3 | Lighthouse Projects | Email & Communication | Configure Gemini meeting summarization for key meetings | Fermin | IT | — | Meeting notes automation live | High | Tech Integrations | EXECUTE | 2026-09-06 | 2026-09-21 | Not Started
80 | Phase 3 | Lighthouse Projects | Email & Communication | Reduce executive email volume: build routing & filtering rules | Fermin | IT / Executives | — | Email volume reduction measurable | High | Processes | EXECUTE | 2026-09-11 | 2026-09-26 | Not Started
81 | Phase 3 | Lighthouse Projects | ClickUp Activation | Restructure ClickUp workspace architecture | Fermin | IT / Ops | Team Leads | ClickUp architecture redesigned | Critical | Tech Integrations | BUILD | 2026-09-01 | 2026-09-21 | Not Started
82 | Phase 3 | Lighthouse Projects | ClickUp Activation | Activate ClickUp Brain across priority workspaces | Fermin | IT | — | ClickUp Brain operational | High | Tech Integrations | BUILD | 2026-09-18 | 2026-10-01 | Not Started
83 | Phase 3 | Lighthouse Projects | ClickUp Activation | Build 5 priority workflow automations in ClickUp | Fermin | IT / Ops | — | 5 automations live | High | Tech Integrations | BUILD | 2026-09-21 | 2026-10-11 | Not Started
84 | Phase 3 | Lighthouse Projects | Asset Quick Win | Pilot asset cataloging system (1 warehouse, top 100 assets) | Fermin | Warehouse / Ops | — | Asset catalog pilot live | High | Data | BUILD | 2026-09-18 | 2026-10-16 | Not Started
85 | Phase 3 | Process Optimization | SOP Modernization | Document current-state SOPs for priority workflows | Fermin | Ops / Team Leads | — | Current-state SOPs documented | High | Processes | BUILD | 2026-09-06 | 2026-10-01 | Not Started
86 | Phase 3 | Process Optimization | SOP Modernization | Design future-state SOPs with automation touchpoints | Fermin | Ops / Team Leads | — | Future-state SOPs designed | High | Processes | BUILD | 2026-09-26 | 2026-10-22 | Not Started
87 | Phase 3 | Process Optimization | Sales-Production Alignment | Design capacity visibility dashboard for sales | Fermin | Sales / Production | IT | Dashboard design approved | Critical | Data | BUILD | 2026-09-18 | 2026-10-06 | Not Started
88 | Phase 3 | Process Optimization | Sales-Production Alignment | Build & deploy capacity visibility tool | Fermin | IT / Sales | Production | Capacity dashboard live | Critical | Tech Integrations | BUILD | 2026-10-01 | 2026-10-31 | Not Started
89 | Phase 3 | Process Optimization | Sales-Production Alignment | Define estimation improvement framework | Fermin | Sales / Finance | — | Estimation framework documented | High | Processes | BUILD | 2026-10-06 | 2026-10-26 | Not Started
90 | Phase 3 | Process Optimization | Cross-Office Standardization | Align workflows across Toronto, Boston, Cleveland | Fermin | Office Leads | Ops | Standardized workflow set | High | Processes | BUILD | 2026-10-01 | 2026-11-15 | Not Started
91 | Phase 3 | Process Optimization | Automation Engine | Build remaining 5-10 priority automations (approvals, handoffs, notifications) | Fermin | IT / Ops | — | 10-15 total automations live | High | Tech Integrations | BUILD | 2026-10-11 | 2026-11-29 | Not Started
92 | Phase 3 | Data Foundation | Asset Intelligence | Define asset taxonomy and classification schema | Fermin | Ops / Warehouse | — | Asset taxonomy defined | High | Data | BUILD | 2026-09-18 | 2026-10-06 | Not Started
93 | Phase 3 | Data Foundation | Asset Intelligence | Scale asset cataloging across all 3 warehouses | Fermin | Warehouse Teams | Ops | Full asset inventory operational | High | Data | BUILD | 2026-10-18 | 2026-11-29 | Not Started
94 | Phase 3 | Data Foundation | Executive Dashboards | Design executive dashboard (unified operational view) | Fermin | Leadership | IT | Dashboard design approved | Critical | Data | EXECUTE | 2026-10-01 | 2026-10-22 | Not Started
95 | Phase 3 | Data Foundation | Executive Dashboards | Build & deploy executive dashboard | Fermin | IT | — | Executive dashboard live | Critical | Tech Integrations | EXECUTE | 2026-10-18 | 2026-11-15 | Not Started
96 | Phase 3 | Data Foundation | Client Intelligence | Design client intelligence structure (history, patterns, verticals) | Fermin | Sales / Marketing | — | Client data model defined | Medium | Data | CREATE | 2026-10-18 | 2026-11-05 | Not Started
97 | Phase 3 | Data Foundation | Project Profitability | Design project profitability tracking framework | Fermin | Finance / Leadership | — | Profitability model defined | High | Data | EXECUTE | 2026-10-22 | 2026-11-10 | Not Started
98 | Phase 3 | Data Foundation | Project Profitability | Deploy profitability tracking in ClickUp/M365 | Fermin | Finance / IT | — | Profitability tracking live | High | Tech Integrations | EXECUTE | 2026-11-05 | 2026-11-29 | Not Started
99 | Phase 3 | People & Adoption | Champions Program | Recruit & onboard internal champions (3-5 per department) | Fermin | HR / Leadership | Team Leads | Champions identified & onboarded | Critical | People & Culture | CREATE | 2026-09-06 | 2026-09-26 | Not Started
100 | Phase 3 | People & Adoption | Champions Program | Train champions on ClickUp, Gemini, and new workflows | Fermin | Champions | IT | Champions trained & certified | Critical | People & Culture | BUILD | 2026-09-26 | 2026-10-16 | Not Started
101 | Phase 3 | People & Adoption | Champions Program | Champions lead peer training in their departments | — | Champions | Fermin | Peer training sessions completed | High | People & Culture | EXECUTE | 2026-10-18 | 2026-11-29 | Not Started
102 | Phase 3 | People & Adoption | Segmented Training | Design segmented training paths (execs, ops, creative) | Fermin | HR | — | Training curriculum by role | High | People & Culture | CREATE | 2026-09-18 | 2026-10-06 | Not Started
103 | Phase 3 | People & Adoption | Segmented Training | Executive training: dashboards, AI tools, decision support | Fermin | Leadership Team | — | Executive training completed | High | People & Culture | EXECUTE | 2026-10-06 | 2026-10-26 | Not Started
104 | Phase 3 | People & Adoption | Segmented Training | Operations training: ClickUp workflows, automations, SOPs | Fermin | Ops / Team Leads | Champions | Ops training completed | High | People & Culture | BUILD | 2026-10-18 | 2026-11-15 | Not Started
105 | Phase 3 | People & Adoption | Segmented Training | Creative training: ClickUp Brain, Gemini for ideation, concept libraries | Fermin | Creative Team | Champions | Creative training completed | High | People & Culture | CREATE | 2026-10-18 | 2026-11-15 | Not Started
106 | Phase 3 | People & Adoption | Change Management | Deploy change communication plan (why, what, how, when) | Fermin | Executive Sponsor | HR | Change comms launched | High | People & Culture | ALL | 2026-09-06 | 2026-09-21 | Not Started
107 | Phase 3 | People & Adoption | Change Management | Conduct adoption pulse checks (bi-weekly survey) | Fermin | HR / Champions | — | Adoption metrics tracked | Medium | People & Culture | EXECUTE | 2026-10-01 | 2026-12-15 | Not Started
108 | Phase 3 | Compliance Framework | AI Governance | Draft AI governance policy (approved tools, data rules, guardrails) | Fermin | Leadership / Legal | IT | AI governance policy draft | Critical | Compliance | EXECUTE | 2026-09-18 | 2026-10-11 | Not Started
109 | Phase 3 | Compliance Framework | AI Governance | Validate & approve AI governance policy with leadership | Fermin | Executive Sponsor | Legal | AI governance policy approved | Critical | Compliance | EXECUTE | 2026-10-11 | 2026-10-22 | Not Started
110 | Phase 3 | Compliance Framework | Data Handling | Define data handling standards (client IP, internal IP, vendor data) | Fermin | Legal / IT | — | Data handling standards documented | High | Compliance | EXECUTE | 2026-09-26 | 2026-10-18 | Not Started
111 | Phase 3 | Compliance Framework | IP Protection | Design IP protection strategy (Dean: 'valuation is in the IP') | Fermin | Legal / Leadership | — | IP protection framework | High | Compliance | EXECUTE | 2026-10-01 | 2026-10-26 | Not Started
112 | Phase 3 | Compliance Framework | AI Content Controls | Define internal controls for AI-generated content | Fermin | Leadership / Legal | — | AI content review workflow defined | High | Compliance | EXECUTE | 2026-10-18 | 2026-11-05 | Not Started
113 | Phase 3 | Compliance Framework | Regulatory Readiness | Assess regulatory requirements (pharma, healthcare clients) | Fermin | Legal / Compliance | — | Regulatory gap assessment | Medium | Compliance | EXECUTE | 2026-10-22 | 2026-11-10 | Not Started
114 | Phase 3 | Platform Integration | M365 Expansion | Expand M365 from finance to org-wide collaboration | Fermin | IT / Finance | Leadership | M365 collaboration deployed | High | Tech Integrations | BUILD | 2026-10-01 | 2026-11-15 | Not Started
115 | Phase 3 | Platform Integration | Global Core Alignment | Connect Global Core (M365) with Operations (ClickUp) | Fermin | IT | Ops / Finance | Systems integrated | High | Tech Integrations | BUILD | 2026-10-18 | 2026-11-29 | Not Started
116 | Phase 3 | Platform Integration | Creative Memory | Build proposal & concept library (searchable archive) | Fermin | Creative / Sales | IT | Creative memory system live | High | Data | CREATE | 2026-10-31 | 2026-12-14 | Not Started
PHASE 4 — STABILIZATION & ADVISORY (Remote)
117 | Phase 4 | Adoption Reinforcement | Measurement | Measure adoption rates across all tools and workflows | Fermin | IT / Champions | HR | Adoption dashboard live | Critical | Data | EXECUTE | 2027-01-01 | 2027-01-11 | Not Started
118 | Phase 4 | Adoption Reinforcement | Measurement | Identify adoption gaps by department, role, and office | Fermin | Champions / HR | — | Adoption gap analysis | High | People & Culture | EXECUTE | 2027-01-08 | 2027-01-15 | Not Started
119 | Phase 4 | Adoption Reinforcement | Targeted Intervention | Design targeted interventions for low-adoption areas | Fermin | HR / Champions | — | Intervention plan by segment | High | People & Culture | EXECUTE | 2027-01-11 | 2027-01-23 | Not Started
120 | Phase 4 | Adoption Reinforcement | Targeted Intervention | Conduct booster training sessions (role-specific) | Fermin | Champions | — | Booster sessions completed | High | People & Culture | EXECUTE | 2027-01-15 | 2027-02-03 | Not Started
121 | Phase 4 | Adoption Reinforcement | Champion Maturation | Transition champions from trained users to internal coaches | Fermin | Champions | HR | Champion coaching model active | High | People & Culture | EXECUTE | 2027-01-11 | 2027-02-03 | Not Started
122 | Phase 4 | Measurement & Reporting | ROI Tracking | Measure Phase 3 ROI against baseline scorecard | Fermin | Finance / Leadership | — | ROI measurement report | Critical | Data | EXECUTE | 2027-01-01 | 2027-01-23 | Not Started
123 | Phase 4 | Measurement & Reporting | ROI Tracking | Quantify time savings from automations and AI tools | Fermin | Ops / IT | — | Automation impact report | High | Data | EXECUTE | 2027-01-08 | 2027-01-23 | Not Started
124 | Phase 4 | Measurement & Reporting | ROI Tracking | Quantify asset reuse savings vs. rebuild costs | Fermin | Ops / Finance | Warehouse | Asset reuse ROI report | High | Data | BUILD | 2027-01-11 | 2027-01-26 | Not Started
125 | Phase 4 | Measurement & Reporting | Scorecard Update | Update transformation scorecard (v3 — post-Implementation) | Fermin | — | — | Transformation Scorecard v3 | Critical | Data | EXECUTE | 2027-01-19 | 2027-01-30 | Not Started
126 | Phase 4 | Measurement & Reporting | Executive Reporting | Deliver executive transformation report to leadership | Fermin | Executive Sponsor | Leadership Team | Executive transformation report | Critical | Data | EXECUTE | 2027-01-30 | 2027-02-03 | Not Started
127 | Phase 4 | Optimization | Workflow Tuning | Optimize automations based on usage data and feedback | Fermin | IT / Ops | Champions | Automations optimized | High | Tech Integrations | BUILD | 2027-01-11 | 2027-02-03 | Not Started
128 | Phase 4 | Optimization | Workflow Tuning | Refine SOPs based on actual adoption patterns | Fermin | Ops / Team Leads | — | SOPs v2 (refined) | High | Processes | BUILD | 2027-01-15 | 2027-02-07 | Not Started
129 | Phase 4 | Optimization | Dashboard Tuning | Refine executive dashboards based on leadership feedback | Fermin | Leadership | IT | Dashboards v2 (refined) | Medium | Data | EXECUTE | 2027-01-11 | 2027-01-30 | Not Started
130 | Phase 4 | Optimization | AI Tuning | Optimize Gemini and ClickUp Brain configurations | Fermin | IT | Champions | AI tools optimized | High | Tech Integrations | EXECUTE | 2027-01-23 | 2027-02-07 | Not Started
131 | Phase 4 | Knowledge Transfer | Documentation | Document all configurations, workflows, and architecture decisions | Fermin | IT | — | Technical documentation complete | Critical | Tech Integrations | ALL | 2027-01-11 | 2027-02-03 | Not Started
132 | Phase 4 | Knowledge Transfer | Documentation | Create internal playbook for ongoing transformation | Fermin | — | Champions | Internal transformation playbook | Critical | Processes | ALL | 2027-01-23 | 2027-02-07 | Not Started
133 | Phase 4 | Knowledge Transfer | Handover | Train internal team to manage and evolve ClickUp architecture | Fermin | IT / Champions | — | Internal team self-sufficient | Critical | Tech Integrations | BUILD | 2027-01-26 | 2027-02-07 | Not Started
134 | Phase 4 | Knowledge Transfer | Handover | Train internal team on dashboard maintenance and data governance | Fermin | IT / Finance | — | Dashboard ownership transferred | High | Data | EXECUTE | 2027-01-26 | 2027-02-07 | Not Started
135 | Phase 4 | Knowledge Transfer | Handover | Transfer AI governance ownership to designated internal team | Fermin | Legal / Leadership | IT | AI governance ownership transferred | High | Compliance | EXECUTE | 2027-01-30 | 2027-02-07 | Not Started
136 | Phase 4 | Advisory | Strategic Advisory | Monthly strategic advisory sessions (ongoing) | Fermin | Executive Sponsor | Leadership | Monthly advisory sessions | High | Processes | ALL | 2027-02-16 | 2027-06-30 | Not Started
137 | Phase 4 | Advisory | Strategic Advisory | Quarterly transformation scorecard review | Fermin | Leadership Team | — | Quarterly scorecard updates | High | Data | ALL | 2027-02-16 | 2027-06-30 | Not Started
138 | Phase 4 | Advisory | Strategic Advisory | Annual digital maturity reassessment | Fermin | Leadership Team | — | Annual maturity report | High | Data | ALL | 2027-06-08 | 2027-06-30 | Not Started

## Summary
TRANSFORMATION ROADMAP — SUMMARY
Phase | Period | Format | Tasks | Critical Tasks | Primary C/B/E
Phase 0 — Pre-Engagement | Mar 18 – Apr 15, 2026 | Remote | 20 | 1 | ALL
Phase 1 — Intake | May 1 – Jun 30, 2026 | Remote | 28 | 3 | CREATE
Phase 2 — Discovery | Jul 1 – Aug 31, 2026 | Onsite Toronto + Remote | 29 | 10 | CREATE
Phase 3 — Implementation | Sep 1 – Dec 15, 2026 | Hybrid | 39 | 10 | BUILD
Phase 4 — Stabilization | Jan 1 – Jun 30, 2027 | Remote / Advisory | 22 | 7 | EXECUTE
TOTAL |  |  | 138 | 31
TASKS BY DIMENSION
Dimension | Tasks | % of Total
People & Culture | 29 | 21%
Processes | 37 | 27%
Tech Integrations | 29 | 21%
Data | 30 | 22%
Compliance | 13 | 9%
TASKS BY C/B/E PHASE
C/B/E Phase | Tasks | % of Total
CREATE | 45 | 33%
BUILD | 36 | 26%
EXECUTE | 31 | 22%
ALL | 26 | 19%

## Methodology Reference
CONSULTING FRAMEWORKS — METHODOLOGY REFERENCE
Framework | Source | Key Principle Applied | Where in Roadmap | Tasks
Lighthouse Projects | McKinsey 4Ds | Quick wins that self-fund and build momentum | Phase 3: Lighthouse workstream | Email triage, ClickUp restructure, asset pilot
No-Regret Moves | BCG DAI | Prioritize initiatives that deliver value regardless of future direction | Phase 1→3: Quick wins shortlist → implementation | Gemini, ClickUp Brain, basic automations
Capability Hexagon | Deloitte | Never implement tech without assessing Talent, Process, Governance | Phase 1: Maturity Assessment (5 dimensions scored 1-5) | Dimension scoring tasks × 5
De-risk Phase | McKinsey 4Ds | Embed change, measure, transfer knowledge | Phase 4: Knowledge Transfer + Advisory | Documentation, handover, coaching
Cultural Change First | McKinsey (46% cite as #1) | Address people before technology | Phase 3: Champions program before tech rollout | Champions onboarded Week 1 of Phase 3
Transformation Scorecard | BCG DAI | Quantitative maturity scoring for benchmarking progress | Phase 1→2→4: Scorecard v1→v2→v3 | 3 scorecard iterations across program
Segmented Adoption | Deloitte Talent Dimension | Different approaches for different roles/generations | Phase 3: Segmented Training paths | Exec, Ops, Creative training tracks
Data Centricity | Accenture TER | Build data collection into every solution from day one | Phase 3: Data Foundation workstream | Asset intelligence, dashboards, profitability
People-Process-Tech-Data-Gov | Industry Standard | 5-pillar assessment framework | All phases: Dimension column maps every task | Every task tagged to 1 of 5 dimensions