## Hoja 1
Phase | Workstream | Step / Area | Task | Owner (Transformaz) | Owner (Taylor) | Support | Output / Deliverable | Priority | Dependencies | Start Date | End Date | Status
Phase 0 | Scope | Transformation Scope Definition | Define transformation objectives with leadership | Fermin | Executive Sponsor | — | Agreed transformation objectives | High | — | 2026-03-18 | 2026-03-22 | Not Started
Phase 0 | Scope | Transformation Scope Definition | Define workstreams in scope (Ops, Tech, Org, etc.) | Fermin | Leadership Team | — | Workstreams defined | High | Define transformation objectives with leadership | 2026-03-20 | 2026-03-25 | Not Started
Phase 0 | Scope | Transformation Scope Definition | Define deliverables by phase | Fermin | — | — | Deliverables framework | High | Define workstreams in scope (Ops, Tech, Org, etc.) | 2026-03-22 | 2026-03-27 | Not Started
Phase 0 | Scope | Scope Alignment | Align expectations with executive team | Fermin | Executive Sponsor | — | Scope alignment confirmed | High | Define deliverables by phase | 2026-03-25 | 2026-03-31 | Not Started
Phase 0 | Scope | Scope Documentation | Draft scope document | Fermin | — | — | Scope document v1 | High | Align expectations with executive team | 2026-03-28 | 2026-04-02 | Not Started
Phase 0 | Scope | Scope Documentation | Finalize and validate scope | Fermin | Executive Sponsor | — | Final scope document | High | Draft scope document | 2026-04-02 | 2026-04-05 | Not Started
Phase 0 | Governance | Governance Design | Define governance structure (Sponsor, SteerCo, etc.) | Fermin | Executive Sponsor | — | Governance model defined | High | Finalize and validate scope | 2026-03-25 | 2026-03-30 | Not Started
Phase 0 | Governance | Governance Design | Define decision-making framework | Fermin | Leadership Team | — | Decision model defined | High | Define governance structure (Sponsor, SteerCo, etc.) | 2026-03-27 | 2026-04-02 | Not Started
Phase 0 | Governance | Cadence & Communication | Define meeting cadence | Fermin | — | — | Meeting cadence defined | Medium | Define governance structure (Sponsor, SteerCo, etc.) | 2026-03-30 | 2026-04-03 | Not Started
Phase 0 | Governance | Cadence & Communication | Define communication channels & formats | Fermin | — | — | Communication model | Medium | Define governance structure (Sponsor, SteerCo, etc.) | 2026-03-30 | 2026-04-04 | Not Started
Phase 0 | Ways of Working | SLA Definition | Define response times & turnaround expectations | Fermin | Ops / Key Stakeholders | — | SLA defined | High | Define governance structure (Sponsor, SteerCo, etc.), Define decision-making framework | 2026-04-01 | 2026-04-05 | Not Started
Phase 0 | Ways of Working | Tools & Collaboration | Define tools (Drive, Asana, Slack, etc.) | Fermin | IT / Ops | — | Tools stack agreed | Medium | Define response times & turnaround expectations | 2026-04-01 | 2026-04-06 | Not Started
Phase 0 | Ways of Working | Working Model | Define sync vs async model | Fermin | — | — | Ways of Working doc | High | Define response times & turnaround expectations | 2026-04-02 | 2026-04-07 | Not Started
Phase 0 | Staffing | Team Structure | Define team structure (Project Lead, Workstream Leads, Analysts) | Fermin | — | — | Team structure defined | High | Finalize and validate scope | 2026-03-28 | 2026-04-02 | Not Started
Phase 0 | Staffing | Resource Allocation | Define allocation by phase | Fermin | — | — | Allocation plan | High | Define team structure (Project Lead, Workstream Leads, Analysts) | 2026-04-01 | 2026-04-06 | Not Started
Phase 0 | Staffing | Internal Alignment | Confirm availability of key resources | Fermin | — | Internal Team | Resource confirmation | High | Define allocation by phase | 2026-04-03 | 2026-04-08 | Not Started
Phase 0 | Contract | Commercial Model | Define pricing model | Fermin | — | — | Pricing structure | High | Finalize and validate scope | 2026-03-25 | 2026-03-30 | Not Started
Phase 0 | Contract | Contract Drafting | Draft agreement | Fermin | Legal | Legal | Draft contract | High | Define pricing model, Finalize and validate scope | 2026-03-30 | 2026-04-05 | Not Started
Phase 0 | Contract | Negotiation | Align terms with client | Fermin | Legal / Sponsor | — | Terms agreed | High | Draft agreement | 2026-04-05 | 2026-04-12 | Not Started
Phase 0 | Contract | Signature | Execute contract | Fermin | Executive Sponsor | — | Signed agreement | Critical | Align terms with client | 2026-04-10 | 2026-04-15 | Not Started
Phase 1 | Data Room Setup | Structure Definition | Define data room structure | Fermin | IT / Ops | — | Data room architecture defined | High | — | 2026-05-01 | 2026-05-03 | Not Started
Phase 1 | Data Room Setup | Repository Setup | Set up data room repository (Drive/Notion/etc.) | Fermin | IT / Ops | — | Data room live | High | Define data room structure | 2026-05-02 | 2026-05-05 | Not Started
Phase 1 | Information Request | Request Framework | Define information request framework | Fermin | — | — | Structured request template | High | Define data room structure | 2026-05-01 | 2026-05-04 | Not Started
Phase 1 | Information Request | Data Collection | Send structured information request to Taylor | Fermin | Executive Sponsor | — | Information request sent | High | Define information request framework | 2026-05-04 | 2026-05-05 | Not Started
Phase 1 | Information Request | Data Collection | Collect SOPs and process documentation | Fermin | Ops / Team Leads | — | SOP repository | High | Send structured information request to Taylor | 2026-05-05 | 2026-05-15 | Not Started
Phase 1 | Information Request | Data Collection | Collect org charts and role definitions | Fermin | HR / Leadership | — | Org structure documentation | High | Send structured information request to Taylor | 2026-05-05 | 2026-05-12 | Not Started
Phase 1 | Information Request | Data Collection | Collect tech stack and systems overview | Fermin | IT | — | Systems inventory | High | Send structured information request to Taylor | 2026-05-05 | 2026-05-12 | Not Started
Phase 1 | Access & Systems | Access Provisioning | Provide system access (tools, platforms) | — | IT / Ops | — | Access granted to systems | Critical | Set up data room repository (Drive/Notion/etc.) | 2026-05-05 | 2026-05-10 | Not Started
Phase 1 | Access & Systems | Tools Familiarization | Access and explore systems | Fermin | — | — | Initial system understanding | High | Provide system access (tools, platforms) | 2026-05-06 | 2026-05-15 | Not Started
Phase 1 | Documentation Review | Process Review | Review SOPs and process documentation | Fermin | — | — | Process insights documented | High | Collect SOPs and process documentation | 2026-05-08 | 2026-05-20 | Not Started
Phase 1 | Documentation Review | Org & Decision Review | Review org structure and roles | Fermin | — | — | Org insights documented | High | Collect org charts and role definitions | 2026-05-08 | 2026-05-18 | Not Started
Phase 1 | Documentation Review | Data & Communication Review | Review systems and data flows | Fermin | — | — | Systems insights documented | High | Collect tech stack and systems overview, Access and explore systems | 2026-05-10 | 2026-05-20 | Not Started
Phase 1 | Initial Mapping & Hypotheses | Workflow Mapping | Map core workflows (initial) | Fermin | — | — | Initial workflow maps | High | Review SOPs and process documentation | 2026-05-15 | 2026-05-25 | Not Started
Phase 1 | Initial Mapping & Hypotheses | Decision Mapping | Map decision-making flows | Fermin | — | — | Decision flow maps | High | Review org structure and roles | 2026-05-15 | 2026-05-25 | Not Started
Phase 1 | Initial Mapping & Hypotheses | Hypothesis Building | Build initial hypotheses (gaps, frictions) | Fermin | — | — | Hypothesis set v1 | High | Map core workflows (initial), Map decision-making flows, Review systems and data flows | 2026-05-20 | 2026-05-28 | Not Started
Phase 1 | Initial Mapping & Hypotheses | Hypothesis Building | Define discovery plan (interviews, on-site focus) | Fermin | Executive Sponsor | — | Discovery plan defined | Critical | Build initial hypotheses (gaps, frictions) | 2026-05-25 | 2026-05-30 | Not Started
Phase 2 | Discovery Planning | Planning & Coordination | Finalize discovery agenda and schedule | Fermin | Executive Sponsor | Ops / HR | Confirmed agenda & calendar | High | Define discovery plan (interviews, on-site focus) | 2026-06-01 | 2026-06-05 | Not Started
Phase 2 | Discovery Planning | Planning & Coordination | Confirm stakeholder participation (interviews & sessions) | Fermin | HR / Leadership | — | Stakeholder list confirmed | High | Finalize discovery agenda and schedule | 2026-06-02 | 2026-06-06 | Not Started
Phase 2 | On-site Execution | Kickoff | Conduct kickoff session (Discovery phase) | Fermin | Executive Sponsor | Leadership Team | Discovery kickoff completed | High | Confirm stakeholder participation (interviews & sessions) | 2026-06-07 | 2026-06-07 | Not Started
Phase 2 | Interviews | Executive Interviews | Conduct leadership interviews | Fermin | Leadership Team | — | Leadership insights documented | Critical | Conduct kickoff session (Discovery phase) | 2026-06-07 | 2026-06-14 | Not Started
Phase 2 | Interviews | Functional Interviews | Conduct functional/team interviews | Fermin | Team Leads | — | Functional insights documented | Critical | Conduct kickoff session (Discovery phase) | 2026-06-08 | 2026-06-18 | Not Started
Phase 2 | On-site Execution | Operational Observation | Observe operations on-site (incl. warehouse) | Fermin | Ops Team | — | Operational observations documented | Critical | Conduct kickoff session (Discovery phase) | 2026-06-08 | 2026-06-18 | Not Started
Phase 2 | Validation | Workflow Validation | Validate workflows with teams | Fermin | Team Leads | — | Validated workflow maps | High | Map core workflows (initial), Conduct functional/team interviews | 2026-06-12 | 2026-06-22 | Not Started
Phase 2 | Validation | Decision Validation | Validate decision-making processes | Fermin | Leadership Team | — | Validated decision maps | High | Map decision-making flows, Conduct leadership interviews | 2026-06-12 | 2026-06-22 | Not Started
Phase 2 | Validation | Systems Validation | Validate systems usage and gaps | Fermin | IT / Ops | — | Systems validation insights | High | Review systems and data flows, Conduct functional/team interviews | 2026-06-12 | 2026-06-22 | Not Started
Phase 2 | Analysis | Gap Identification | Identify gaps, redundancies and breakdowns | Fermin | — | — | Gap analysis draft | Critical | Validate workflows with teams, Validate decision-making processes, Validate systems usage and gaps | 2026-06-18 | 2026-06-25 | Not Started
Phase 2 | Interviews | Follow-up Interviews | Conduct follow-up interviews (remote/hybrid) | Fermin | Stakeholders | — | Additional insights captured | Medium | Identify gaps, redundancies and breakdowns | 2026-06-20 | 2026-06-30 | Not Started
Phase 2 | Analysis | Synthesis | Consolidate discovery findings | Fermin | — | — | Consolidated findings | Critical | Identify gaps, redundancies and breakdowns | 2026-06-25 | 2026-07-02 | Not Started
Phase 2 | Validation | Executive Validation | Validate findings with leadership | Fermin | Executive Sponsor | Leadership Team | Validated findings | Critical | Consolidate discovery findings | 2026-07-02 | 2026-07-07 | Not Started
Phase 2 | Reporting | Reporting | Draft current state report | Fermin | — | — | Current state report v1 | High | Validate findings with leadership | 2026-07-05 | 2026-07-12 | Not Started
Phase 2 | Reporting | Reporting | Finalize current state & diagnosis report | Fermin | Executive Sponsor | — | Final diagnosis report | Critical | Draft current state report | 2026-07-12 | 2026-07-31 | Not Started